## Fall
GANTT CHART | [24 empty] | https://goo.gl/PXLbMe
PROJECT TITLE | Team 11 Digit EEG Classifier
[5 empty] | PHASE ONE | [13 empty] | PHASE TWO | [34 empty] | PHASE THREE
TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | 2021-09-27 | [6 empty] | 2021-10-04 | [6 empty] | 2021-10-11 | [6 empty] | 2021-10-18 | [6 empty] | 2021-10-25 | [6 empty] | 2021-11-01 | [6 empty] | 2021-11-08 | [6 empty] | 2021-11-15 | [6 empty] | 2021-11-22 | [6 empty] | 2021-11-29 | [6 empty] | 2021-12-06
[5 empty] | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U
Project Proposal
Introduction & Background | Ben, Mehul | 2021-09-27 | 2021-10-04 | 7 | bar: 2021-09-27 M to 2021-09-27 U
Problem Definition | Ben, Mehul | 2021-09-27 | 2021-10-04 | 7 | bar: 2021-09-27 M to 2021-09-27 U
Methods | Johannes, Ishan | 2021-09-27 | 2021-10-04 | 7 | bar: 2021-09-27 M to 2021-09-27 U
Potential Results & Discussion | Felipe | 2021-09-27 | 2021-10-04 | 7 | bar: 2021-09-27 M to 2021-09-27 U
Video Recording | All | 2021-10-04 | 2021-10-07 | 3 | bar: 2021-10-04 M to 2021-10-04 W
GitHub Page | Johannes, Ishan, Ben, Felipe | 2021-10-04 | 2021-10-07 | 3 | bar: 2021-10-04 M to 2021-10-04 W
Model 1
Data Sourcing and Cleaning | Ben, Felipe | 2021-10-07 | 2021-10-15 | 8 | bar: 2021-10-04 R to 2021-10-11 R
Model Selection | Johannes, Ishan | 2021-10-15 | 2021-10-18 | 3 | bar: 2021-10-11 F to 2021-10-11 U
Data Pre-Processing | Johannes, Ishan | 2021-10-18 | 2021-10-25 | 7
Model Coding | Ben, Felipe | 2021-10-25 | 2021-11-08 | 13 | bar: 2021-10-25 M to 2021-11-01 U
Results Evaluation and Analysis | Mehul | 2021-11-08 | 2021-11-16 | 8 | bar: 2021-11-08 M to 2021-11-15 M
Midterm Report | All | 2021-11-08 | 2021-11-16 | 8 | bar: 2021-11-08 M to 2021-11-15 M
Model 2
Data Sourcing and Cleaning | Ben, Felipe | 2021-10-18 | 2021-10-22 | 4 | bar: 2021-10-18 M to 2021-10-18 R
Model Selection | Johannes, Ishan | 2021-10-22 | 2021-10-25 | 3 | bar: 2021-10-18 F to 2021-10-18 U
Data Pre-Processing | Johannes, Ishan | 2021-10-25 | 2021-10-29 | 4 | bar: 2021-10-25 M to 2021-10-25 R
Model Coding | Ben, Felipe | 2021-10-25 | 2021-11-19 | 24 | bar: 2021-10-25 F to 2021-11-01 U; 2021-11-15 T to 2021-11-15 R
Results Evaluation and Analysis | Mehul | 2021-11-19 | 2021-11-24 | 5 | bar: 2021-11-15 F to 2021-11-22 T
Model 3
Data Sourcing and Cleaning | Ben, Felipe | 2021-10-18 | 2021-10-22 | 4 | bar: 2021-10-18 M to 2021-10-18 R
Model Selection | Johannes, Ishan | 2021-10-22 | 2021-10-25 | 3 | bar: 2021-10-18 F to 2021-10-18 U
Data Pre-Processing | Johannes, Ishan | 2021-10-25 | 2021-10-29 | 4 | bar: 2021-10-25 M to 2021-10-25 R
Model Coding | Ben, Felipe | 2021-10-25 | 2021-11-19 | 24 | bar: 2021-10-25 F to 2021-11-01 U; 2021-11-15 T to 2021-11-15 R
Results Evaluation and Analysis | Mehul | 2021-11-19 | 2021-11-24 | 5 | bar: 2021-11-15 F to 2021-11-22 T
Evaluation
Model Comparison | All | 2021-11-29 | 2021-12-07 | 8 | bar: 2021-11-29 M to 2021-12-06 M
Presentation | All | 2021-11-29 | 2021-12-06 | 7 | bar: 2021-11-29 M to 2021-11-29 U
Recording | All | 2021-12-06 | 2021-12-07 | 1 | bar: 2021-12-06 M
Final Report | All | 2021-11-29 | 2021-12-07 | 8 | bar: 2021-11-29 M to 2021-12-06 M

## Proposal Contributions
Name | Proposal Contributions
Ishan Sheth | Methods, Gantt Chart, Contribution Table, Video Recording
Johannes Qian | Methods, GitHub Page, Video Recording
Felipe Bergerman | Potential Results & Discussion, GitHub Page, Video Recording
Mehul Dhoot | Introduction & Background, Problem Definition, Video Recording
Benjamin Madar | Introduction & Background, Problem Definition, Gantt Chart, Contribution Table, Video Recording

## Fall Overview
GANTT CHART | [7 empty] | https://goo.gl/PXLbMe
PROJECT TITLE | Team 11 Digit EEG Classifier
[5 empty] | PHASE ONE |  | PHASE TWO | [5 empty] | PHASE THREE
TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | 2021-09-27 | 2021-10-04 | 2021-10-11 |  | 2021-10-18 | 2021-10-25 | 2021-11-01 | 2021-11-08 | 2021-11-15 | 2021-11-22 | 2021-11-29 | 2021-12-06
Project Proposal |  | 2021-09-27 | 2021-10-07 | 10
Introduction & Background | Karishma | 2021-09-27 | 2021-10-04 | 7
Problem Definition | Tim | 2021-09-27 | 2021-10-04 | 7
Methods | Bryan | 2021-09-27 | 2021-10-04 | 7
Potential Results & Discussion | Noah & Gabby | 2021-09-27 | 2021-10-04 | 7
Video Recording | All | 2021-10-04 | 2021-10-07 | 3
GitHub Page | Karishma | 2021-10-04 | 2021-10-07 | 3
Model 1 |  | 2021-10-07 | 2021-11-16 | 39
Data Sourcing and Cleaning | Tim | 2021-10-07 | 2021-10-15 | 8
Model Selection | Karishma | 2021-10-15 | 2021-10-18 | 3
Data Pre-Processing | Tim | 2021-10-18 | 2021-10-25 | 7
Model Coding | Karishma | 2021-10-25 | 2021-11-08 | 13
Results Evaluation and Analysis | Tim | 2021-11-08 | 2021-11-16 | 8
Midterm Report | All | 2021-11-08 | 2021-11-16 | 8
Model 2 |  | 2021-10-18 | 2021-11-24 | 36
Data Sourcing and Cleaning | Gabby | 2021-10-18 | 2021-10-22 | 4
Model Selection | Noah | 2021-10-22 | 2021-10-25 | 3
Data Pre-Processing | Gabby | 2021-10-25 | 2021-10-29 | 4
Model Coding | Noah | 2021-10-25 | 2021-11-19 | 24
Results Evaluation and Analysis | Gabby | 2021-11-19 | 2021-11-24 | 5
Model 3 |  | 2021-10-18 | 2021-11-24 | 36
Data Sourcing and Cleaning | Bryan | 2021-10-18 | 2021-10-22 | 4
Model Selection | Bryan | 2021-10-22 | 2021-10-25 | 3
Data Pre-Processing | Bryan | 2021-10-25 | 2021-10-29 | 4
Model Coding | Bryan | 2021-10-25 | 2021-11-19 | 24
Results Evaluation and Analysis | Bryan | 2021-11-19 | 2021-11-24 | 5
Evaluation |  | 2021-11-24 | 2021-12-07 | 13
Model Comparison | Tim | 2021-11-29 | 2021-12-07 | 8
Presentation | All | 2021-11-29 | 2021-12-06 | 7
Recording | All | 2021-12-06 | 2021-12-07 | 1
Final Report | All | 2021-11-29 | 2021-12-07 | 8